## Sheet1
SNO | Problem / Description | Status | Developer Comments | Client's Comments | QA Comments | Final Status
1 | Homeowner - Logged in | done |  |  | done
| Tabs to use, and in order - which should also be stickied. Please rename all tabs to follow the below: | done |  |  | done
| Post Project | done |  |  | done
| My Projects | done |  |  | done
| My Reviews | done |  |  | done
| Messages | done |  |  | done
| Favourites | done |  |  | done
| Homii Tips | Done |  |  | done
| Incentives | done |  |  | done
| Edit Profile | done |  |  | done
2 | When a top tab is clicked, it should remain the same Orange as when it’s hovered over. | done | Designer |  | done
| Basically, anything that can be CLICKED on the site, when hovered over, the text should change colour (or give some indicator to the user that they can click). | done | Designer |  | done
3 | Default image = Homii Magnifying Glass | done | Designer
| THIS SHOULD NEVER CHANGE. | done | Designer
5 | We should make the user icon image at the top right hand the Homii Magnifyging Glass | done | Designer
6 | When I click Logout, for some reason, I need to click it twice... | done | Dev |  | done
7 | We like that when a homeowner logs in (after their initial login, which will prompt the video to display), they are directed towards the “Post Project” page. | Pending
8 | Within the current “Create Project” the final button should read “POST,” as there are no future steps when a user is already logged in. | Done |  |  | done
9 | Within the current “Project List” tab: | done |  |  | done
| We should make the individual fields underneath Delete & Mark As Complete as a blank box, in which the user will check mark when actioning either item. This will should then trigger a second alert asking if the user is sure of their action (FOR BOTH DELETE & MARK AS COMPLETE) | Done |  |  | fix also on contractor
| We should alert user’s that “Marking this as complete/Deleting this job, is for your own reference and will only be reflected on your profile” | Pending
| We should remove the “EDIT” function, since this will not be changing on a contractor’s side, it’s kind of irrelevant. What do you think? | Pending
| When you click into “Contractor Matches,” the user should be able to click anywhere on the contractor’s box to get into their profile. Not just on their Company name. | Done |  |  | Mark Contractor not match
| The tabs within should read “OPEN PROJECTS” & “COMPLETED PROJECTS” | Done |  |  | done
| As well, POST A NEW PROJECT button should be a larger box and in a similar font. Maybe we place it somewhere else on the page? | Pending | designer
| OR, why don’t we get rid of this altogether? Since the top bar has a POST PROJECT button always showing….? | Pending
| At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this | done |  |  | done
| consistent throughout. | done |  |  | done
13 | Within the “Incentives” tab: | done |  |  | done
| ○ We don’t need to display an image, and we especially shouldn’t give an option to add, since a homeowner will never display their image publically… If this is to fill space, please use the default Homii Magnifyging Glass. | Done |  |  | not done
| ○ Let’s call it an “Incentive ID” | Done |  |  | Done
| ○ We don’t need to display the user’s Email ID, unless I’m missing something? No | Done |  |  | Done
| ○ I want to have more of the URL showing in the box with the unique referral code. We can move the URL underneath a button saying “Copy your unique referral code:” | Done |  |  | done
| ○ Please make the “Share to Social ICONS” smaller | done | Designer |  | done
| ○ Total Due & Amount Earned” should be swapped, and “Request Payment” should be written a few sizes smaller. As well, please change the colour of Request Payment to a darker colour. Orange doesn’t look great. | done | Designer |  | done
14 | Both dollar amounts should have “$” before them. | done |  |  | done
15 | NOTE: Request Payment, should be underneath/inside the “Amount Due” box. | done | designer |  | done
16 | Within the “Reviews” tab: | done |  |  | done
| Reviews should display the Contractor Company Name, not the individual who signed up. | done |  |  | done
| ○ Since we can only click on the Company Name to get to a contractor’s profile, we need to make it OBVIOUS that that is where to click. Maybe change the colour to underline it, make the font bigger, etc… | Pending
17 | We want this to be as easy as possible! Please use your expertise here. | Pending
| ○ As discussed, we’ll add another action item on this page to prompt homeowner to write a review for another company. | Pending
18 | ● Within the “Favourite Contracto” tab: | done |  |  | done
| ○ What will be displayed? Currently, you’re showing a review? What if this homeowner hasn’t review a favourited contractor? | Pending
| ○ I think we should display a brief overview of the contractor’s business, with the information they’ve provided upon signup | Pending
19 | ■ Show Company Name, Avg. Star Ratings, Categories offered, Message/Chat option, Phone number, Review, and Company logo/picture. | Pending
20 | ■ When I click on for example, avg. star ratings, I should be taken to that company’s reviews. When I click on Messages, it should go to chat. When I click on the phone number (from mobile) it should call the company. When I click on review, it should allow me to write a review. Etc, etc, etc,. | Pending
21 | ● This goes for all content on site basically. If you see a contractors name somewhere, you should be able to click on them. Or their reviews, etc. | Pending
22 | ● Within the current “Chat” tab: | Pending
| We have questions for SendBird and need a company email before we can setup a call with them. | Pending
23 | We don’t like the look of it right now. Seems like it would | Pending
24 | ● Within the current “Edit Profile” tab: | done |  |  | done
| ○ When I click “Change Password,” we MUST force the user to input their CURRENT PASSWORD first. Only then can they change their password. | Pending |  |  | done
25 | ■ Thus, the fields will read: | Pending |  |  | done
26 | ● Current Password | Pending |  |  | done
27 | ● New Password | Pending |  |  | done
28 | ● Confirm New Password | Pending |  |  | done
| Contractor - Logged in | Pending
29 | Tabs to use (which should also be stickied). Please rename all tabs to follow the below: | Pending |  | This section is missing completely!
| ○ My Projects | Done |  |  | done
| ○ My Reviews | Pending
| ○ Messages | Done |  |  | done
| ○ Incentives | Done |  |  | done
| ○ Homii Tips | done |  |  | done
| ○ Edit Profile | Done |  |  | done
30 | When a top tab is clicked, it should remain the same Orange as when it’s hovered over. | Pending | Designer |  | done
31 | ● We should make the user icon image at the top right hand the Homii Magnifyging Glass | Pending | Designer
32 | ● When I click Logout, for some reason, I need to click it twice... | Pending | Designer |  | done
33 | ● Default image = Homii Magnifying Glass | Pending | Designer
| ○ They should be triggered to change this image. | Pending | Designer
34 | ● Within the current “Project List” tab: | done
| ○ Firstly, there will only be two tabs within: “My Projects” AND “Completed Projects” | Done |  |  | done
| ○ We want to keep these categories within this tab (for the search result box): | Pending
34 | ■ Job Title | Pending
35 | ■ Job Description | Pending
36 | ■ Estimated Budget | Pending
37 | ■ Estimated Start Date | Pending
38 | ■ City | Pending
39 | ■ View | Pending
40 | ● This is basically giving all the same information that we’re already displaying… WE WANT TO TALK ABOUT AN EASIER WAY TO DISPLAY THIS INFO...why have it twice??? I like the “VIEW” but if it doesn’t show it nicely, then….. It kinda sucks.. | Pending
| ○ Would be nice if they could view as PDF or something, and | Pending
| then send to email, print, etc. | Pending
41 | Chat | Pending
42 | ● Should read “Message Homeowner” | Pending
43 | Mark as Complete (should be an empty box, and with a “did you mean to mark as complete” similar to the homeowner setup). | Pending
44 | ● We should tell contractor’s “Marking this complete is for your own reference, and enables you to track your Return on Investment with Homii, and will only be reflected on your profile”” | Pending
| ○ Remove “Categories” & “Status”...What is Status even??? | Pending
| ○ Within the Completed Jobs tab: | Pending
45 | ■ This is where we discussed showing some analytics for the contractor, around how much they earned. | Pending
46 | ■ Maybe instead of showing “Estimated Budget,” we should have it read “Estimated Revenue” | Pending
47 | ● Can we make it so that when a contractor Marks a Job Complete, we force them to input how large the project was in $$??? | Pending
| ○ This will allow us to track properly, as well as give the contractor a realistic view on how well this is working for them. | Pending
48 | We’ll remove Categories from this list too. | Pending
49 | ● Within the “Incentives” tab: SAME AS HOMEOWNER INCENTIVE NOTES | Pending |  |  | done
50 | ● Within the current “Chat” tab: SAME AS HOMEOWNER INCENTIVE NOTES | Pending
51 | ● Within the current “My Profile” tab: | Pending
| ○ Let’s make the Toggle buttons smaller at the top - they’re too big right now | Pending
| ○ Within the forms, all of the fonts and boxes seem so large. Let’s reduce the size a little bit and make it easier to get through. | Pending
| ○ Let’s have buttons read “Edit Private Information” AND “Edit Company Information” | Pending |  |  | done
52 | ■ Under “Edit Private Information” we should include: | Pending |  |  | Done
53 | ● First Name | Pending |  |  | done
54 | ● Last Name | Pending |  |  | done
55 | ● Phone Number | Pending |  |  | done
56 | ● Postal Code | Pending |  |  | done
57 | ● Email Address | Pending |  |  | done
58 | ● Password | Pending |  |  | remove password field and set button only
59 | ● Change Password | Pending
| ○ When I click “Change Password,” we MUST force the user to input their CURRENT PASSWORD first. Only then can they change their password. | Pending
58 | ■ Thus, the fields will read: | Pending |  |  | done
59 | ● Current Password | Pending |  |  | done
60 | ● New Password | Pending |  |  | done
61 | ● Confirm New Password | Pending |  |  | done
62 | ■ Under “Edit Company Information” we should include: | Pending
63 | ● The Company Logo/Icon, which we are NOT showing in the Edit Profile | Pending
67 | The Gallery Images, which we are NOT showing in the Edit Profile | Pending
68 | ● Everything else that we currently have, except let’s add the “Upload Company Logo” & “Gallery Images” towards the top. | Pending
| ○ What fields are mandatory here? What will a public facing profile look like if a | Pending
| user doesn’t complete any of their company info? | Pending
| Referrer - Logged in | Pending
69 | There will be NO TABS / 2nd header for a Referrer. | Pending
70 | ● We should make the user icon image at the top right hand the Homii Magnifyging Glass | Done
71 | ● When I click Logout, for some reason, I need to click it twice... | Done
72 | ● Default image = Homii Magnifying Glass | Done
| ○ THIS SHOULD NEVER CHANGE. | Done
73 | ● Within the “Incentives” tab: SAME AS HOMEOWNER INCENTIVE NOTES | Done
| System Admin - Logged in | Pending
74 | Tabs to use (which should also be stickied). Please rename all tabs to follow the below: | Pending
| ○ Projects | done
| ○ Reviews | done
| ○ Categories | done
| ○ Cities | done
| ○ Provinces | done
| ○ Incentives? | Pending
75 | ■ We need to add an incentive category for us. | Pending
76 | ■ We should have access to incentives as well, in case we need to manually manipulate? If system doesn’t capture something | Pending
77 | ■ As well, we want this to be able to collect all the data: | Pending
78 | ● Total amount paid out, with the option to change the date range | Pending
| ○ System User | Pending
79 | ● When a top tab is clicked, it should remain the same Orange as when it’s hovered over.We should make the user icon image at the top right hand the Homii Magnifyging Glass | Pending | Designer
80 | ● When I click Logout, for some reason, I need to click it twice… | Pending
81 | ● Within the “Project List” tab: | Done
| ○ We want to see some statistics here: | Done
81 | ■ Total Jobs posted (this month, this year, etc.) | done |  |  | done
82 | ■ I know we can count the pages, however, onc we are larger, that won’t be feasible. | Pending
| ○ Nothing is populating in the search results, and we are unable to test the Actions here… | Pending
83 | ■ What we REQUIRE is: ability to Edit (Add or remove any text or images | Pending
| to an already existing project, which should populate on the contractor | Pending
| and homeowner site), Delete completely, or Post Brand New (for a homeowner). | Pending
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | Done |  |  | done
84 | ● Within the “Cities” tab: | done
| ○ As long as the cities we add will fall into the backend matching algorithm, as well as the payment gateway, then we’re all set. | done |  |  | NOT DONE
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | done
85 | ● Within the “Provinces” tab: | done
| ○ As long as the cities we add will fall into the backend matching algorithm, as well as the payment gateway, then we’re all set. | done
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | done
86 | ● Within the “Categories” tab: | done
| ○ How does the Category Charge work? How will this tie into the backend payment system? | done |  |  | NOT DONE
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | done |  |  | done
87 | ● Within the “System User” tab: | done
| ○ We want to have statistics here, showing us: | Pending
88 | ■ Total Revenue earned (this month, this year, etc.) | Done |  |  | done
89 | ■ Total Referrer $$ Earned / Owed (this month, this year, etc.) | Done |  |  | done
90 | ■ Visitor to site this month | Pending
91 | ■ Total Homeowner count | Done |  |  | done
92 | ■ Total Contractor Count | Done |  |  | done
93 | ■ Total Referrer Count | Done |  |  | done
94 | ■ Will BrainTree offer something for this? | Pending
| ○ What do the actions do on this page? The one action and then the “amount” button? | Pending
| ○ How will we know if a user has paid? How will we know if a user’s CC is expired/expiring? | Pending
| ○ Can we make homeowner’s / referrer’s inactive as well? Or is it just Contractors? | Pending
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, | Pending
| colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | Pending
95 | ● Within the “Homeowner Review” tab: | Done
| ○ We need a search function here, so that we can quickly find and address bad/false reviews | Pending
| ○ Please change the two action buttons here into one single button, since they do the same thing (allow the Admin to View & Edit). You can call it “VIEW” | Pending
| ○ At the bottom of the results, we couldn’t see how the “PREVIOUS” & “NEXT” button will look when hovered over or clicked. However, we don’t like the size, colour, or text as it current is. Please make it visually appealing, and keep this consistent throughout. | Pending
96 | ● WordPress | Pending
| ○ What will this look like for us? Where will we access? | Pending
| ○ What pages will fall under WordPress? | Pending
| Basic user - NOT Logged in | done
97 | ● When I click “POST A PROJECT,” from the homepage, there are typos on the fields. | Done
| ○ Both buttons are different sizes….. We need to keep consistent throughout the entire site! | Done
| ○ “Job Description” is incorrectly spelt | Done
| ○ “Estimated State Date” should all be capitalized | Done
| ○ “ATTACH FILE(S)” needs to be displayed differently, because right now it looks like it could be a “previous” button… how can we show it so that it’s clear? | Done |  |  | allow to add multiple files at a time and images should show images and name
98 | ` | Done
| ○ When I click on “Estimated Budget,” we need to have a dropdown similar to TrustedPros - to make it easier for homeowners to select a budget, and for us to track estimated project size. See image below. Please copy fields | Done
| ○ When a user clicks “NEXT,” it should take them to the CREATE YOUR ACCOUNT / TELL US ABOUT YOURSELF ‹ the same as the TrustedPros setup. We can have ours in 2 steps, or 1. Your call. | Pending
99 | ■ When a user completes this “Step 1,” they can either fill out their information to create an account & post project all in one, OR, they can click “Already have an account? Sign in.” and then their project will be automatically posted and put into their account. | Pending
100 | ● When signing up, for ALL USER TYPES, they must have a duplicate Password field to ensure accuracy. As well, they need a duplicate Email field to ensure accuracy. | Pending
101 | ● When signing up, specifically for CONTRACTORS, we must display all 4 of these below for them to click and agree to. | Pending
102 | ● There is nowhere to Review a contractor that we can see as of yet, however, this should be available for any user who is not logged in. See TrustedPros process ‹ https://trustedpros.ca/write-a-review | Pending
| ○ We want to follow the same process as them. See what it looks like to “search for | Pending
| a contractor and write a review” without having an account. | Pending
Footer & Header
Header:
103 | ● Can we see what it would look like if we reduced the size of the house in the logo? | Done | Designer
104 | ● Header should always be stickied | Done | Designer
105 | ● Entire should be centered | Done | Designer
106 | ● Let’s move the logo down so that the writing is centered with the search bar & sign up/login. It’s okay that the bottom of the magnifying glass sticks lower. | Done
107 | ● Search functionality should always provide a dropdown to the user based on the fields that match the letters being typed. As more letters are added, less results will show, until finally, the one result being typed to completion will be displayed. | Pending
108 | ● SIGNUP button: will go to a page that has the two large boxes side by side displaying (HOMEOWNER) or (CONTRACTOR) and below them, we will have a smaller box showing (REFERRER) ‹ see Trustedpros for reference… it’s similar, minus the. referrer section. | Pending | Designer
| Footer: | Done
109 | ● Homeoner | Done
| ○ Login/Signup | Done
| ○ Post Project | Pending
110 | Reviews | Pending
| ○ Write A Review | Pending
| ○ Search Contractors/Categories | Pending
| ○ Incentives | Pending
| ○ Tips For Hiring ‹ video | Pending
111 | ■ Please make this on WordPress so that we can make changes | Pending
| ○ Review Guidelines | Pending
112 | ● Contractor | Done
| ○ Login/Signup | Done
| ○ Incentives | Pending
| ○ Pricing | Pending
| ○ Code Of Conduct | Pending
| ○ Tips ‹ video | Pending
113 | ■ Please make this page on WordPress so that we can make changes | Pending
114 | 1 | Pending
| ○ Login/Signup | Pending
| ○ Tips ‹ video | Pending
115 | ■ What’s in it for them, what’s in it for them | Pending
116 | ■ Please make this page on WordPress so that we can make changes | Pending
117 | ● Homii | Done
| ○ About | Done
| ○ Blog | Done
| ○ Contact Us | Pending
| ○ Terms & Conditions | Pending
| ○ Review Guidelines | Pending
| ○ Code of Conduct | Pending
118 | ● We’ll create our social media links towards the end | Pending | Designer
119 | ● Please change text in footer, underneath logo to read “All Rights Reserved (little R in circle)2020 homii” | Done
120 | ● Can we see what it would look like if we reduced the size of the house in the logo? | Done
| BrainTree Information | Pending
121 | ● Created a sandbox account, as per the BrainTree’s suggestion | Pending
122 | ● We will create our live business account once we’re all confirmed with the testing | Pending
| ○ Sandbox details: | Pending |  | ■ Username: yourhomii@gmail.com
|  | Pending |  | ■ Password: X1T3YEDfeu*u
| SendBird Information | Pending
123 | ● Created a free account using my personal email, since they will not allow us to start a paid service until we have our company emails purchased and setup. | Pending
124 | ● See details below: | Pending |  | ○ Username: yourhomii@gmail.com
○ Password: eWpKY%7u8ULF
Change password button disable
all Edit Button Disable
Edit Company Page In Bussiness Since

## Sheet2
issues
We should alert user’s that “Marking this as complete/Deleting this job, is for your own reference and will only be reflected on your profile”
We should remove the “EDIT” function, since this will not be changing on a contractor’s side, it’s kind of irrelevant. What do you think?
Within the “Incentives” tab:
○ We don’t need to display an image, and we especially shouldn’t give an option to add, since a homeowner will never display their image publically… If this is to fill space, please use the default Homii Magnifyging Glass.
○ Let’s call it an “Incentive ID”
○ We don’t need to display the user’s Email ID, unless I’m missing something?
○ I want to have more of the URL showing in the box with the unique referral code. We can move the URL underneath a button saying “Copy your unique referral code:”
Within the “Reviews” tab:
Reviews should display the Contractor Company Name, not the individual who signed up.
○ Since we can only click on the Company Name to get to a contractor’s profile, we need to make it OBVIOUS that that is where to click. Maybe change the colour to underline it, make the font bigger, etc…
We want this to be as easy as possible! Please use your expertise here.
○ As discussed, we’ll add another action item on this page to prompt homeowner to write a review for another company.
● Within the “Favourite Contracto” tab:
○ What will be displayed? Currently, you’re showing a review? What if this homeowner hasn’t review a favourited contractor?
○ I think we should display a brief overview of the contractor’s business, with the information they’ve provided upon signup
■ Show Company Name, Avg. Star Ratings, Categories offered, Message/Chat option, Phone number, Review, and Company logo/picture.
■ When I click on for example, avg. star ratings, I should be taken to that company’s reviews. When I click on Messages, it should go to chat. When I click on the phone number (from mobile) it should call the company. When I click on review, it should allow me to write a review. Etc, etc, etc,.
● This goes for all content on site basically. If you see a contractors name somewhere, you should be able to click on them. Or their reviews, etc.
● Within the “System User” tab:
○ We want to have statistics here, showing us:
■ Total Revenue earned (this month, this year, etc.)
■ Total Referrer $$ Earned / Owed (this month, this year, etc.)